## Task_Table
ID | Zadania | PM | AM | AI | DMC | DG1 | DG2 | DG3 | DG4 | T | UE | LM
1 | Interviews with Airport Management
2 | Gathering System Requirements
3 | Gathering Requirments about Customer Management Modules
4 | Gathering Requirements about Airport Management Modules
5 | Gathering Requirements about Personel and Flight Management
6 | Gathering Information about Other Airport Working Systems
7 | Preliminary Analyzis
8 | Preliminary Required Skill Identification
9 | Preliminary Required Item/Software
10 | Preliminary Cost Identification
11 | Forming Team
12 | Recruiting People
13 | Asigning People to roles
14 | Functional Specification Creation
15 | Defining Desired Modules
16 | Defining System Functionality
17 | Preliminary Software Specification
18 | Preliminary Risk and Risky Modules Recognition
19 | Defining Modules Expectations
20 | Defining System Modules
21 | Defining Authorization Module
22 | Defining Customer Management Module
23 | Defining Planes Management Module
24 | Defining Flight Management Module
25 | Defining Security Management Module
26 | Defining Personel Management Module
27 | Defining Remote Access Module
28 | Defining Communication Module
29 | Defining System Functionality
30 | Defining Functionality of each Module
31 | Defining GUI interface
32 | Defining Each Subsystem Functionality
33 | Create Development Plan
34 | Conceptual Design
35 | Logical Design
36 | Physical Design
37 | Create Test Plan
38 | Create User Education Plan
39 | Non Functional Specification
40 | Defining Software Expectation and Functionalities
41 | Defining Hardware Functionality/Expectations
42 | Defining Hardware Needs
43 | Defining Software Needs
44 | Creating Authorization Module
45 | Defining Additional Module 1 Specification And Desires
46 | Develop Component
47 | Test Component
48 | Creating Customer Management Module
49 | Defining Additional Module 1 Specification And Desires
50 | Develop Component
51 | Test Component
52 | Creating Planes Management Module
53 | Defining Additional Module 1 Specification And Desires
54 | Develop Component
55 | Test Component
56 | Creating Flight Management Module
57 | Defining Additional Module 1 Specification And Desires
58 | Develop Component
59 | Test Component
60 | Creating Personel Management Module
61 | Defining Additional Module 1 Specification And Desires
62 | Develop Component
63 | Test Component
64 | Creating Remote Access Module
65 | Defining Additional Module 1 Specification And Desires
66 | Develop Component
67 | Test Component
68 | Creating Communication Module
69 | Defining Additional Module 1 Specification And Desires
70 | Develop Component
71 | Test Component
72 | Creating Security Management Module
73 | Defining Additional Module 1 Specification And Desires
74 | Develop Component
75 | Test Component
76 | Internal Release #1
77 | Test components
78 | Test integrated application
79 | GUI Development
80 | Release #1
81 | Testing Functionality
82 | Gathering Client Notices
83 | Stabilizing
84 | Bug Tracking
85 | Testing
86 | User Education
87 | Client Management Fase
88 | Documentation
89 | Introduce Fase
90 | Care/Support Fase
Project Manager = PM
Developer group = DG
Analyzis Manager = AM
Tester = T
Design Manager/Coordinator = DMC
User Education = UE
Analyzer/Interviewer = AI
Logistic Manager = LM
SUPPORT
RESPONSIBLE

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | Windows User Account | Max Units | Standard Rate | Cost Per Use | Notes
1 | Development | D | Work |  |  |  |  | 100% | 0,00 zł/hr | 0
2 | Logistics management | L | Work |  |  |  |  | 100% | 0,00 zł/hr | 0
3 | Testing | T | Work |  |  |  |  | 100% | 0,00 zł/hr | 0
4 | User education | U | Work |  |  |  |  | 100% | 0,00 zł/hr | 0
5 | Program management | P | Work |  |  |  |  | 100% | 0,00 zł/hr | 0
6 | Product management | P | Work |  |  |  |  | 100% | 0,00 zł/hr | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Internal Release #1 | Development | 0% | 152 hrs | 100%
Internal Release #n | Development | 0% | 152 hrs | 100%

## Info_Table
Microsoft Project | Template ID: | 9876543210 | (Do Not Edit)
Microsoft Project is a project management program designed to help you plan and manage your projects and communicate project information.
Whether you have a simple list of tasks or want to coordinate activities across multiple projects, Microsoft Project makes it easy to get started and learn as you go.
With this template you can export data to Excel to perform more advanced numerical analysis. Then you can import project data back into Microsoft Project to perform standard project tasks, such as:
* Seeing your tasks linked in a Gantt Chart
* Seeing how much work each person on the team has assigned to them
You can easily import this information back into Microsoft Project and keep working without reentering data.